## Checklist
Cricket Gear Reuse Schemes: General Checklist 1.0 3-12-23
A resource created by The Centre for Sustainable Design, University for the Creative Arts
Question: what does success look like for this project? increased access [Golden Triangle] - 3 Smart Goals: social; economic; environmental?
Budgets: what will be the costs? who pays for what?
What is the catchment: local area / district(s); 'feeder' clubs [for larger clubs]; clubs in a specific league; various state primary/secondary & prep/public schools
Project website: https://cfsd.org.uk/projects/crg/ - do you set up a local CGR webpage for engagement, guidance and resources
Note: highlighted cells are for emphasising fundamentally important issues for planning & implementing the CGR project and process
Date | Task | Responsibility | Specifics | Notes
Deposit (drop-off) & Sorting / Quality Assessment
People
| Define lead coordinator / staff roles & responsibilities |  | See Briefing note: Roles & Responsibilities for CGR schemes | Oversight; leadership; volunteer & stakeholder engagement; coordination; comms; budget management
| Define Volunteer roles & responsibilities |  | See Briefing note: Roles & Responsibilities for CGR schemes | Define roles/tasks/responsibilities: who does what?
| Volunteers - signing-up |  | Process/form | Identify & Sign-up volunteers for drop/collection events & other roles In addition to any staff for larger clubs.
| Deposit stage Risk Assessment / H&S |  | TBC | Risk assessment for volunteers; club / personal liability; for donors and users; for project
Process
| Agree dates & times (drop-off, sorting, collection, surplus/exccees to LT) |  |  | e.g. possibly Easter holidays - might have a multiple 'drop off ' dates and ongoing reuse service offer
| Drop-off location |  | Visit the space/assess layout | Decide on drop-off location & logistics
| > Trial: drop-off |  | If needed i.e. generally for larger schemes / first year | e.g. Easter holiday
| > Main: drop-off |  |  | e.g. Easter holiday
| Assess, plan and agree drop-off & storage/security |  | Agree drop-off system e.g. where people go, who collects, process, etc | Where & how will the gear be dropped-off e.g. Club House and stored tempoarily/longer-term; how much gear will come in (difficult to forecast)?
| Set-up / layout drop-off location & system |  | Establish mechanism to sort gear - see also quality control | Set-up location / room / system for drop-off layout beforehand - consider any sorting / categories: adult - male & female / youth - male & female / kids - male & female; different types of cricket gear
| Quality assessment & Separation of cricket gear |  | Flow diagram | Separate out different types of cricket gear: adult - male & female / youth - male & female / kids - male & female;
| Quality control process |  | Policy including exclusions & damaged gear (PPE)/briefing note for volunteers | Remove / Refuse gear not 'fit for purpose' - show due diligence - develop simple test - get ahead of PPE regulations; identify where Not FFP gear goes;
| Exclusions |  | Document | Helmets, clothing & shoes/boots (unless clean) to be excluded in the local reuse offer/but if helmets do come-in store as LT will take for overseas reuse? (decision to be made)
| Damaged items |  | Flow diagram/storage location for LT (Lords Taverners) collection | Damaged but usable gear will be taken by LT
Comms
| Promotion (within club/wider) |  | Draft emails/whatsapp/social media messages | Clarity on what is being taken / excluded; Integrate into existing events & communication channels e.g. Spond, engagement activities, webpage e.g. any club campaigns, pre-season nets, AGM, etc
| Publicity/PR - local press; local & wider stakeholders |  | Press release to media in catchment area/build local & cricket press lists | Identify local press in the catchment area & wider cricket press/podcasts; social media
| Stakeholder engagement e.g. schools, clubs, etc |  | Define groups/engage/define 'wishlist' of gear | Define key partners / stakeholders e.g. local schools; comms to parters and stakeholders
| Partner/sponsor engagement |  | Agree focus areas/level of engagement
| Filming |  | Volunteer completes filming/edits | Project video
| Project website |  | Set-up page on club / partner website(s)
Administration
| Documentation & data capture |  | Produce wishlist form/inventory system/product form | Documenting desposited cricket gear: digital systems e.g. excel; paper systems
| Email / mobile phone capture |  | Wishlist form to include name/organisation/email/phone for follow-up
| Costs of deposit process / management |  | Define costs | Hire / borrowing of ton bags / cages? refreshments for volunteers, launch, depsoit sessions, ; etc
| Insurance |  | TBC
Collection
People
| Define staff roles & responsibilities |  | Briefing note | Oversight; leadership; volunteer & stakeholder engagement; coordination; comms; budget management
| Define Volunteer roles & responsibilities |  | Briefing note | Define roles/tasks/responsibilities: who does what? e.g. welcome desk, cricket gear table managers & floating person
| Volunteers - signing-up |  | Process/form | Identify volunteers. In addition to 3 x FTE, who wants to get involved in 'drop model' supervision
| Collection stage Risk Assessment / H&S |  | Use /or adapt an existing relevant Risk / H&S form | Risk assessment for volunteers; club / personal liability; for donors and users; for project
Process
| Demand & supply |  |  | Pre-collection - Identify batch requests among state schools & disadvantaged teams e.g. 10 batting pads, 10 gloves, etc [define specific collection process]
| * Key stakeholders |  |  | Determine who these area e.g. schools; smaller / lower league / neighbouring clubs in areas of disadvantage etc
| * Disadvantaged target groups |  | Define above - contact for wishlist | Key estates or neighbourhoods; Afghan refugees; How to assess disadvantage; how to avoid collection for re-sale on eBay, etc
| Set the Rules |  | Agreement between partners on items in the wishlist e.g. 10 pads, etc | How many items a) per organisation and b) per person
| Launch event? |  | Develop plan | Perhaps tie-in with another event &/or 2nd session - invite personalities/ex-players - food/drink
| Target date(s) & event times |  |  | e.g. Possibly around Easter - might be a couple of weeks/multiple collection dates and ongoing reuse service offer
| Trial: collection |  | Limited promition - aim to test the system/individual roles
| Main: collection (organisations) |  | Batch collection by / delivery to schools, etc | Plan and agree process for batch collection or delivery; approval process for schools?
| Main: collection (individuals) |  |  | e.g. Easter holiday
| Room layout |  | Visit the room/assess layout | Plan / agree and set-up room layout beforehand: adult - male & female / youth - male & female / kids - male & female; different types of cricket gear
| Customer journey at event |  | Process diagram e.g. meet at front desk, given product form & add details, visiting product table, tick items taken, etc | Prepare forms (downloadable/hard copy) with cricket gear listed, manufacturer, other details with email for follow-up
| Forms & data capture |  | Design forms & collect forms/data input after the event | Collection of product forms; use of excel / google survey or similar
| Collection process - start/operation/close |  | Define start/end time - align to process diagram | Prepare a flow chart: perhaps 1 x test & 2 half or full day sessions
| Excess gear |  | Storage of excess gear & failed gear | Determine storage & destination(s) for remainder gear e.g. LTKRS;
| Storage prior to Lords Taverners collection |  | Location/process - see above | Where?
| Preparation & organisation of Lords Taverners collection |  | Agree collection date/time with LT - what costs LT covers & what club/others cover | Where? Logistics plan as LT need gear bagged & palletised & shrink wrapped [specific process]
Comms
| Disclaimer |  | TBC | Disclaimer needed? e.g. can you borrow and adapt a local Repair Cafe disclaimer?
| Promotion (internal to club / league) |  | Emails, whatsapp, social media | Prepare and plan pre-collection comms; Integrate into existing events & communication channels e.g. Spond, engagement activities e.g. AGM / club dinner, pre-season nets etc
| Promotion (external to club / league) |  | Define & email multipliers in catchment area/club media support?
| PR (external to club / league) |  | Press release to local media / soc media in catchment area | Identify local press in the catchment area & wider cricket press/podcasts
| Stakeholder engagement |  | As above | Define key partners / stakeholders e.g. local schools; comms to parters and stakeholders
| Partner engagement |  | As above
| Filming |  | As above - part of a video project | Project video e.g. for local publicity
Administration
| Documentation & data capture |  | Product form - excel system for data input - data entry [who does it] | Documenting collected cricket gear: digital systems e.g. excel; paper systems
| Email / mobile phone capture |  | Product form to include name/organisation/email/phone for follow-up
| Costs of deposit process / management |  | Define costs | Purchase of Ton bags? Hire of cages? refreshments for volunteers, launch, depsoit sessions, ; etc
| Insurance |  | TBC | What is the existing scope of coverage?
Impact analysis
| Define survey objectives |  | Define/agree
| * Social benefits |  |  | Quantitative (how many benefited, # of players enabled to play, etc) and qualititative data (how they feel about benefits and outcomes)
| * Economic benefits |  |  | Value of gear; project costs / savings; etc
| * Envionmental benefits |  |  | Kg of resources / materials diverted from waste; carbon estimates; etc
| Prepare questionnaire |  | Separate quuestionnaires for organisations & individuals? or combined? | Follow-up emails from the collection event;
| Pilot to test questionnaire test |  | Agree a sample
| Start survey(s) |  | Email survey link to organisations & individuals
| Findings/analysis |  | Excel analysis | Impact asessment: environment, social and economic
| Survey report |  | Report | Complete report: approach supporters
| Analysis of product forms |  | Data input | Analysis of forms (deposit & collection): data input (temp)
| Quantative impact analysis |  | Excel analysis | Products 'in' and products 'out'/landfill diversion/co2e savings
| Impact report |  | Report
| Filming / Video |  | Plan and agree filming including any necessary permissions | Project video; interviews with club officers / staff (larger clubs), volunteers, beneficiaries, stakeholders
| PR for project report and outcomes |  | Press release: local and cricket media | Identify cricket / sport & environmental press; local press (for social & economic benefits); wider cricket press/podcasts

## Gantt
Task | Responsibility
Deposit (drop-off) & Sorting / Quality Assessment |  | w/c 1/1/2024 | w/c 8/1 | w/c 15/1 | w/c 22/1 | w/c 29/1 | w/c 5/2 | w/c 12/2 | w/c 19/2 | w/c 26/2 | w/c 4/3 | w/c 11/3 | w/c 18/3 | w/c 25/3
People
Define staff roles & responsibilities
Define Volunteer roles & responsibilities
Volunteers - signing-up
Deposit stage Risk Assessment / H&S
Process
Agree dates (drop-off, sorting, collection, surplus/exccees to LTKRS)
Assess, plan and agree drop-off & storage/security
Set-up / layout Drop-off location & system
Quality assessment & Separation of cricket gear
Quality control process
Exclusions
Damaged items
Comms
Publicity (within club/wider)
Publicity/PR - local press; local & wider stakeholders
Stakeholder / partner engagement
Filming
Administration
Documentation & Data capture
Any costs of deposit process / management
Collection |  | w/c 1/1/2024 | w/c 8/1 | w/c 15/1 | w/c 22/1 | w/c 29/1 | w/c 5/2 | w/c 12/2 | w/c 19/2 | w/c 26/2 | w/c 4/3 | w/c 11/3 | w/c 18/3 | w/c 25/3
People
Define staff roles & responsibilities
Define Volunteer roles & responsibilities
Volunteers - signing-up
Collection stage Risk Assessment / H&S
Process
Demand & supply
Target date(s)
Room layout
Customer journey at event
Collection event forms & data capture
Launch event
Event process - start/operation/close
Batch collection by / delivery to schools
Excess / remainder gear
Temporary storage prior to LTKRS collection
Preparation & organisation of LT collection
Comms
Disclaimer
Publicity (internal)
PR (external)
Stakeholder / partner engagement
Filming
Administration
Documentation & Data capture
email capture
Any costs of collections process / management
Insurance
Impact analysis |  | w/c 1/1/2024 | w/c 8/1 | w/c 15/1 | w/c 22/1 | w/c 29/1 | w/c 5/2 | w/c 12/2 | w/c 19/2 | w/c 26/2 | w/c 4/3 | w/c 11/3 | w/c 18/3 | w/c 25/3
Online survey of users of the service
Findings/analysis
* Social benefits
* Economic benefits
* Envionmental benefits
Report
Analysis of forms / online survey
Filming
PR for project report and outcomes